## Sheet1
Rule Id | Rule Name | Level | Taxa | Message Ids | Code status | Message status | Notes | Checks still to write:
SARIF1001 | RuleIdentifiersMustBeValid | error | Rules | Default | DONE | READY FOR REVIEW |  | 21
SARIF1002 | UrisMustBeValid | error | Uris | UrisMustConformToRfc3986 | DONE
|  |  |  | FileUrisMustConformToRfc8089 | TODO
|  |  |  | FileUrisMustNotIncludeDotDotSegments | TODO
SARIF1003 | UrisShouldUseConventionalForm | warning | Uris | FileUrisWithoutHostNameShouldUseTripleSlashForm | TODO
SARIF1004 | ExpressUriBaseIdsCorrectly | error | Uris | UriBaseIdRequiresRelativeUri | DONE
|  |  |  | TopLevelUriBaseIdMustBeAbsolute | DONE
|  |  |  | UriBaseIdValueMustEndWithSlash | DONE
|  |  |  | UriBaseIdValueMustNotContainDotDotSegment | TODO
|  |  |  | UriBaseIdValueMustNotContainQueryOrFragment | TODO
SARIF1005 | UriMustBeAbsolute | error | Uris | Default | DONE
SARIF1006 | InvocationPropertiesMustBeConsistent | error | Invocation | EndTimeMustNotPrecedeStartTime | DONE
SARIF1007 | RegionPropertiesMustBeConsistent | error | Regions | EndLineMustNotPrecedeStartLine | DONE | IN PROGRESS
|  |  |  | EndColumnMustNotPrecedeStartColumn | DONE | IN PROGRESS
|  |  |  | RegionStartPropertyMustBePresent | TODO | IN PROGRESS
SARIF1008 | PhysicalLocationPropertiesMustBeConsistent | error | Regions | ContextRegionRequiresRegion | DONE | READY FOR REVIEW
|  |  |  | ContextRegionMustBeProperSupersetOfRegion | DONE | READY FOR REVIEW
SARIF1009 | IndexPropertiesMustBeConsistentWithArrays | error | Arrays | TargetArrayMustExist | DONE
|  |  |  | TargetArrayMustBeLongEnough | DONE
SARIF1010 | RuleIdMustBeConsistent | error | Results | ResultMustSpecifyRuleId | DONE | READY FOR REVIEW
|  |  |  | ResultRuleIdMustBeConsistent | DONE | READY FOR REVIEW
SARIF1011 | ReferenceFinalSchema | error | Schema | Default | DONE
SARIF1012 | MessagePropertiesMustBeConsistent | error | Messages | SupplyCorrectNumberOfArguments | TODO | READY FOR REVIEW
SARIF2001 | AuthorHighQualityMessages | warning | Rules, Messages | IncludeDynamicContent | TODO |  | Accept single quotes only. Validate rule metadata, not results strings.
|  |  |  | EnquoteDynamicContent | TODO
|  |  |  | TerminateWithPeriod | DONE
SARIF2002 | UseMessageArguments | warning | Results, Messages | Default | TODO | READY FOR REVIEW
SARIF2003 | ProduceEnrichedSarif | note | Content | ProvideVersionControlProvenance | TODO |  | Not ready. Needs to be split
|  |  |  | ProvideCodeSnippets | TODO
|  |  |  | ProvideContextRegion | TODO
|  |  |  | ProvideHelpUris | TODO
|  |  |  | EmbedFileContent | TODO
SARIF2004 | OptimizeFileSize | warning | Size | EliminateLocationOnlyArtifacts | TODO
|  |  |  | DoNotIncludeExtraIndexedObjectProperties | TODO
SARIF2005 | ProvideHelpfulToolInformation | note | Tool | ProvideConciseToolName | DONE | IN PROGRESS
|  | warning |  | ProvideToolVersion | DONE | IN PROGRESS
|  | warning |  | UseNumericToolVersions | DONE | IN PROGRESS | Require 2 or more dot-separated numbers, followed by anything at all. We _don't_ validate semanticVersion, which should be a separate check in the same rule, and which in fact could have been in the schema!
SARIF2006 | UrisShouldBeReachable | warning | Uris | Default | TODO
SARIF2007 | ExpressPathsRelativeToRepoRoot | warning |  | Default | TODO
SARIF2008 | ProvideSchema | warning | Schema | Default | DONE
SARIF2009 | UseConventionalSymbolicNames | note |  | UseConventionalRuleIds | TODO | READY FOR REVIEW
|  |  |  | UseConventionalUriBaseIdNames | TODO | READY FOR REVIEW